## Manual User testing
Project name | IFB299 Project
Module Name | Admin Login
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID07 | T26 | Add 'Employee login" link on homepage, which links to login page | CID07_T26_01 | 1. Check for Login Button Acessibilty 2. Click and Check For Functionality on Search page | Valid URL Functional Button | Mouse Click | User Should be succesfully be able to veiw Employee Login Page | Webpage Accessed |  | Pass
|  |  | CID07_T26_02 | 1. Check for Login Button Acessibilty 2. Click and Check For Functionality on Home page | Valid URL Functional Button | Mouse Click | User Should be succesfully be able to veiw Employee Login Page | Webpage Accessed |  | Pass
|  |  | CID07_T26_03 | 1. Check for Login Button Acessibilty 2. Click and Check For Functionality on Login Page | Valid URL Functional Button | Mouse Click | User Should be succesfully be able to veiw Employee Login Page | Webpage Accessed |  | Pass
| T28 | Secure login feature with username and password verification (both frontend and backend verification) | CID07_T28_01 | 1. Input Correct username 2. Input Correct Password 3. Click Log on Button | Valid URL Valid Username and Password | username:admin password:admin | User Should be Succesfully be able to log in and veiw page | Succesfully log in |  | Pass
|  |  | CID07_T28_02 | 1. Input Incorrect username 2. Input Correct Password 3. Click Log on Button | Valid URL Incorrect Username Valid Password | Username: Incorrect_test Password:admin | user Prompted "Incorrect Username or Password. Please try again." | Prompted attempt was incorrect |  | Pass
|  |  | CID07_T28_03 | 1. Input Correct username 2. Input Incorrect Password 3. Click Log on Button | Valid URL Correct Username Incorrect username | Username: admin Password:Incorrect_test | user Prompted "Incorrect Username or Password. Please try again." | Prompted attempt was incorrect |  | Pass
|  |  | CID07_T28_04 | 1. Input Incorrect username 2. Input Incorrect Password 3. Click Log on Button | Valid URL Incorrect Username Incorrect Password | Username:Incorrect_test Password:Incorrect_test | user Prompted "Incorrect Username or Password. Please try again." | Prompted attempt was incorrect |  | Pass
| T29 | Ensure security features such as input sanitization and password hashing | CID07_T29_01 | 1. Input SQL Query into Username and Password 2. Check if any chnages where made | Valid URL Valid SQL Query | "1 AND USER() like 'root%'" | User should be prompeted with incorrect username and password. Also Database and website should not be affected by the input and reain untouched. | Database and website remians the same |  | Pass |  |  | Django has intergrated software to prevent Input Sanitiazation from occuring
|  |  | CID07_T29_02 | 1. Input SQL Query into Username and Password 2. Check if any chnages where made | Valid URL Valid SQL Query | "CREATE TABLE IF NOT EXISTS tasks ( task_id INT AUTO_INCREMENT, title VARCHAR(255) NOT NULL, start_date DATE, due_date DATE, status TINYINT NOT NULL, priority TINYINT NOT NULL, description TEXT, PRIMARY KEY (task_id) ) ENGINE=INNODB;" | User should be prompeted with incorrect username and password. Also Database and website should not be affected by the input and reain untouched. | Database and website remians the same |  | Pass |  |  | Django has intergrated software to prevent Input Sanitiazation
| T30 | Ensure "Cusomters" Link can be seen after logging in | CID_T30_01 | 1. Check to See if Button is Identiiable and easily accesible | Vaild URL Valid Button | Mouse Click | User Should be presented with a page with cusomter iormation inside it | Button is Present |  | Fail |  |  | Button is not Present
| T31 | Ensure "Cusomters" Link is functioning and when clicked a page is brought up with cusomter information | [10 empty] | Not accesable as Button to Customers lin is not Present. No Cusomter page Present.
ID03 | T20 | Check Add Employee Button is Present
| T22 | When "add employee" button brings up page with data entry sections
T23
T24
T25