## Manual User testing
Project name | IFB299 Project
Module Name | Admin Login_ Restrict Info
Created By | Jack McMahon
Creation Date | 2018-09-29
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID07 | T26 | Add 'Employee login" link on homepage, which links to login page | CID07_T26_01 | 1. Check for Login Button Acessibilty 2. Click and Check For Functionality on Search page | Valid URL Functional Button | Mouse Click | User Should be succesfully be able to veiw Employee Login Page | Webpage Accessed |  | Pass
|  |  | CID07_T26_02 | 1. Check for Login Button Acessibilty 2. Click and Check For Functionality on Home page | Valid URL Functional Button | Mouse Click | User Should be succesfully be able to veiw Employee Login Page | Webpage Accessed |  | Pass
|  |  | CID07_T26_03 | 1. Check for Login Button Acessibilty 2. Click and Check For Functionality on Login Page | Valid URL Functional Button | Mouse Click | User Should be succesfully be able to veiw Employee Login Page | Webpage Accessed |  | Pass
| T28 | Secure login feature with username and password verification (both frontend and backend verification) | CID07_T28_01 | 1. Input Correct username 2. Input Correct Password 3. Click Log on Button | Valid URL Valid Username and Password | username:admin password:admin | User Should be Succesfully be able to log in and veiw page | Succesfully log in |  | Pass
|  |  | CID07_T28_02 | 1. Input Incorrect username 2. Input Correct Password 3. Click Log on Button | Valid URL Incorrect Username Valid Password | Username: Incorrect_test Password:admin | user Prompted "Incorrect Username or Password. Please try again." | Prompted attempt was incorrect |  | Pass
|  |  | CID07_T28_03 | 1. Input Correct username 2. Input Incorrect Password 3. Click Log on Button | Valid URL Correct Username Incorrect username | Username: admin Password:Incorrect_test | user Prompted "Incorrect Username or Password. Please try again." | Prompted attempt was incorrect |  | Pass
|  |  | CID07_T28_04 | 1. Input Incorrect username 2. Input Incorrect Password 3. Click Log on Button | Valid URL Incorrect Username Incorrect Password | Username:Incorrect_test Password:Incorrect_test | user Prompted "Incorrect Username or Password. Please try again." | Prompted attempt was incorrect |  | Pass
| T29 | Ensure security features such as input sanitization and password hashing | CID07_T29_01 | 1. Input SQL Query into Username and Password 2. Check if any chnages where made | Valid URL Valid SQL Query | "1 AND USER() like 'root%'" | User should be prompeted with incorrect username and password. Also Database and website should not be affected by the input and reain untouched. | Database and website remians the same |  | Pass |  |  | Django has intergrated software to prevent Input Sanitiazation from occuring
|  |  | CID07_T29_02 | 1. Input SQL Query into Username and Password 2. Check if any chnages where made | Valid URL Valid SQL Query | "CREATE TABLE IF NOT EXISTS tasks ( task_id INT AUTO_INCREMENT, title VARCHAR(255) NOT NULL, start_date DATE, due_date DATE, status TINYINT NOT NULL, priority TINYINT NOT NULL, description TEXT, PRIMARY KEY (task_id) ) ENGINE=INNODB;" | User should be prompeted with incorrect username and password. Also Database and website should not be affected by the input and reain untouched. | Database and website remians the same |  | Pass |  |  | Django has intergrated software to prevent Input Sanitiazation
| T30 | Ensure "Cusomters" Link can be seen after logging in | CID_T30_01 | 1. Check to See if Button is Identiiable and easily accesible | Vaild URL Valid Button | Mouse Click | User Should be presented with a page with cusomter iormation inside it | Button is Present |  | Fail |  |  | Button is not Present
| T31 | Ensure "Cusomters" Link is functioning and when clicked a page is brought up with cusomter information | [10 empty] | Not accesable as Button to Customers lin is not Present. No Cusomter page Present.
ID03 | T20 | Check Add Employee Button is Present
| T22 | When "add employee" button brings up page with data entry sections
T23
T24
T25

## Customer Recomend Car
Project name | IFB299 Project
Module Name | Customer Recomeneded car
Created By | Jack McMahon
Creation Date | 2018-09-24
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID06 | T15 | Putting "Recommended Cars" on the home page | CID06_T15_01 | Ensure Link is Visualy Present | Identifiable Button | mouse clicks | Usser can See Car recomdendations link | Link veiwable |  | pass
|  |  | CID06_T15_02 | Ensure Link Works Correctly and Re-Directs you to the correct page | Functional Button Valid URL | mouse clicks | User will be taken to a car recomdendatoin page | Open recommended cars page |  | pass
| T16 | Implement popup box that is presented to the user when clicked | CID06_T16_01 |  | Identiable popupbox | mouse clicks Sotre-Sydeny Car Make- Toyota REST-NONE | User should be presented with a popup box after link is clicked | Popup box veiwable |  | pass
| T17 | Create SQL query of user ferinement inputted popup | CID06_T17_01 | IF OTHER TASKS WORK IN THE STORY THIS TASK WORKS CORRECTLY | Valid Query Compatibility | mouse clicks Data entry form filled | If all other tasks are working this will be functioning correctly | SQL Theory is correct and funcitoning correctly |  | pass
| T18 | List Cars which match user refined search options on new page | CID06_T18_01 | Ensure Cars Listed match up with results | Veiwable List Reliable cars/data output | mouse click | user should be presented with a page with recommended cars (Based off user refined search) | User will be presented with a lsits of cars which can be further refined |  | pass
| T19 | Add Recommended cars to Individual Page | CID06_T19_01 | Ensure Individual page is generated with car recomdendations | Valid URL Functional Page generation | Mouse click | Car recomdendations are added to each indiviual car page | user can veiw a recommended cars on each individual car info page |  | pass
|  |  |  | Open up a separate page and see if cars are recommended | Valid URL Functional Page generation | Mouse click | Car recomdendations are added to each indiviual car page | user can veiw a recommended cars on each individual car info page
| T20 | Implement Dynamic Filtering option at the top of the page | CID06_T20_01 | Ensure Filtre system is identifable and has proper functionality | Functional Filtre System Identiable/easy to use filtre system | Mouse click | User shold be able to filtre results to better refine their results | user can access and use the filre system which can furhter refine their given results accurately |  | FAIL
| T21 | Verify User Story is complete | CID06_T21_01 | Ensure all tasks are complete | All Tasks Are complete | Mouse click | All tasks are funcitoning correctly | User can use all features and there are all functioning

## Rental Information
Project name | IFB299 Project
Module Name
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID05 | T35 | Add Hirring Patterns under car information for login Employees | CID05_T35_01 | 1. Ensure Hirring Patterns for Employees is Veiwable inside a car info page | Valid and Veiwable Button Secuirty Portected Button (Must be logged in) | Mouse Click | User is able to veiw hirring patterns link succesfully | Link is Veiwbale |  | pass
|  |  | CID05_T35_02 | 1. Ensure Hirring Patterns CANNOT be seen when a employee is NOT logged in | Button is Not Veiwable Information cannot be accessed | Mouse Click | User is able to veiw hirring patterns link succesfully | When Clicked hirring patterns is veiwable |  | pass
| T36 | WRITE TEST CASES | CID05_T36_01 | 1. Write test cases for section | Ensure everything is complete and functioning correctly | Writing Test Cases | Test cases completed and written | Test cases Completed
| T38 | Write SQL Query to find car types from each store location | CID05_T38_01 | 1. Check if it can search and find specific car types from store (location) | Valid and correct SQL Query Car types can be found based of stores location | Mouse Click | SQL query can sort through data and draw out specific data based off user data input | User can seach and find specific car types from store/lcoation |  | pass
| T39 | Display Results of query in tabular format | CID05_T39_01 | 1. Check if data is generated and presented in tabular tabel format 2. Ensure data in table is correct | Table is generated in correct format with correct info Table is veiwable and is presented in a acceptable way | Mouse Click | User can veiw generated table with specific data | Veiwable table |  | pass
| T40 | Show total number of rentals by customer | CID05_T40_01 | 1. Check customers are veiwable 2. Check to see if you can veiw the number of rentals | Customer info is correct Rental Information is Correct | Mouse Click | User can veiw toatl number of rentals | Cusomters are vewiable with their specific renatl history |  | pass
| T41 | Verify Story is complete | CID05_T41_01 | 1. Check all tasks are completed and are all working correctly | Task are completed | Complete all tasks | Test cases are completed and all tasks for ID are Completed (Operational) | All tasks are completed |  | pass

## Finding info on car
Project name | IFB299 Project
Module Name
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID04 | T42 | Write test cases | CID04_T42_01 | 1. Write Test Cases 2 Ensure all Test Cases are complete
| T43 | Add “Search for Car” link/search box for logged in employees | CID04_T43_01 | 1. Logg On 2. Ensure button is veiwbale for logged on employees
|  |  | CID04_T43_02 | 1. Ensure button is not viewbale for users that are not logged on
| T44 | Create employee only API endpoint to search database for any specific entry | CID04_T44_01
| T45 | Create clear car info page | CID04_T45_01
| T46 | Use JQuery request to access API and receive selected cars’ information | CID04_T46_01
| T47 | Create a table which allows dynamic ordering of search results | CID04_T47_01
| T48 | Add method to find which store the car is at | CID04_T48_01
| T49 | Add counter to display number of search results | CID04_T49_01
| T50 | Verify story is complete | CID04_T50_01

## Graphic Representation
Project name | IFB299 Project
Module Name
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID11 | T51 | Select color pattern and style of chart | CID11_T51_01
| T52 | Add pie chart to search page | CID11_T52_01 | 1. Ensure pie chart is veiwable | Veiwable Pie Chart | mouse click/scroll | User Can veiw Pie Chart
| T53 | Write JavaScript to dynamically update chart on search | CID11_T53_01 | 1. Ensure Pie chart updates based off data | Updatable pie Chart | mouse click/scroll | User Can veiw Pie Chart
| T54 | Add pie chart to store page | CID11_T54_01 | 1. Ensure pie chart is veiwable | Veiwable Pie Chart | mouse click/scroll | User Can veiw Pie Chart |  | Pass
| T55 | Write JavaScript to dynamically update chart in page load | CID11_T55_01 | 1. Ensure Pie chart updates based off data | Updatable pie Chart | mouse click/scroll | User Can veiw Pie Chart |  | Pass
| T56 | Add option to switch chart type from pie chart to bar chart | CID11_T56_01
| T57 | Add bar chart to rental history section | CID11_T57_01
| T58 | Add option to change rental history from time to drop off location | CID11_T58_01 | 1. Change graphiocal option 2. check if cahnge is showing correct data | Pie chart is vewiable and data shown can be changed between the options | mouse click/scroll | User can vewi pie/bar chart and the different sets of data (data options)
| T59 | Manually test charts | CID11_T59_01 | 1. Test Suer Cases 2. Complete and write User test cases
| T60 | Verify story is complete | CID11_T60_01 | 1. All task for user story are completed | Tasks are completed |  | All tasks are completed which are associated with user story

## Car Rental History
Project name | IFB299 Project
Module Name
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID10 | T61 | Write test cases | CID10_T61_01 | 1. Write all the test cases | Test cases are completed as wwell as all required tasks | Mouse keyboard |  |  | pass
| T62 | Write class method to find rental history by car ID | CID10_T62_01 | 1. Ensure Class method is written and can search and find cars by ID | Class Method is written and compatable
| T63 | Add “Rental History” for logged in employees (On employee page) | CID10_T63_01 | 1. Ensure Rental history can be vewiable from car info page 2. Ensure when clicked appropriate information is displayed | link and button is veiwable | Valid Button and Link | Valid Button and Link |  | pass
| T64 | Add list of Past Rentals by customer | CID10_T64_01 | 1. Ensure List is Present 2. Ensure list shows appropriate data | List of past rentals is create and veiwable (employees only) | Mouse click | Veiwable table/data |  | pass
| T65 | Allow authorized employees to view past rental information (eg pick up and drop off location) | CID10_T65_01 | 1. Log on 2. Ensure information is vewiable by logged on employees | past rental history is veiwable by logged on employees only | mouse Click Keyboard Logged On Employee: u- admin p- admin | Protected data vewiable by logged on employees only |  | pass
|  |  | CID10_T65_02 | 1. Make sure no one is logged on 2. Ensure information is NOT veiwable (user NOT logged on) | Past rental history Cannot be veiwed if employee is not logged on | Mouse Click Keyboard | Protected data Rental History Not veiwable |  | pass
| T66 | Verify story is complete | CID10_T66_01 | 1. Ensure all tasks are complete for the Story | All tasks are complete for specific story | All tasks are completed for Story | All tasks are completed for Story

## Navigation
Project name | IFB299 Project
Module Name
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID01 | T01 | Create a main landing page | CID01_T01_01 | 1.Check if main landing page has been created | User is taken to a landing page when they first access it (Home Page) | Mouse Click | Valid URL Viewable landing page (Home Page) |  |  | pass
| T02 | Create site theme & template | CID01_T01_02 | 1. Ensure home page has a suitable and appealing design | Home page has a well-executed design which is the main hub for the features of the website (Home page) | Mouse Click | Valid URL Well-designed Home page |  |  | pass
| T03 | Write test cases | CID01_T01_03 | 1. Write Test Cases | All Test Cases Written
| T04 | Create Navigation Bar | CID01_T01_04 | 1. Ensure navigation bar is Viewable | User is able to easy identify the navigation bar as well has be able to succesfully use it | Mouse Click | Viewable navigation bar Navigation Bar contains components |  |  | pass
| T05 | Verify story is complete | CID01_T01_05 |  | All Tasks for Story are complete | Mouse Click Keyboard | All Tasks for Story are complete |  |  | pass

## Finding Cars
Project name | IFB299 Project
Module Name | Finding available cars
Created By | Jack McMahon
Creation Date
Story ID | Task ID | Task Description | Case ID | Test Steps | Preconditions | Test Data | Post Conditions | Expected Results | Actual Results | Status | Executed By | Executed Date | Comments (If Any)
ID02 | T06 | Create page with a tabular layout | CID02_T06_01 | 1. Ensure page has been created 2. Ensure page has a tabular layout | User can view the page which are generated and present in tabular format | Mouse Click |  |  | pass
| T07 | Write test cases | CID02_T07_01 | 1. Write Test Csaes | Test cases written and completed | Mouse Click Keyboard
| T08 | Create database and populate with data | CID02_T08_01 | 1. Create a clear well-desinged functioning Database | Database created with correct data which can be successfully pulled from | Mouse Click Keyboard |  |  | pass
| T09 | Write SQL Query to display only the available cars | CID02_T09_01 | 1. Ensure information is displayed correctly with correct data (SQL theory) | SQL Theory is correct and pulls and display the correct information from the database (Available cars) | Mouse Click Keyboard |  |  | pass
| T10 | Write internal API to handle the SQL query | CID02_T10_01 |  |  | Mouse Click
| T11 | Display available cars in table format | CID02_T11_01 | 1. Search for a Car 2. Check to see if available cars are presented in correct format | User should be able to veiw all available cars | Mouse Click SEARCH: BMW |  |  | pass
| T12 | Display more car details upon clicking each individual car | CID02_T12_01 | 1. Search for a car 2. click a specific car 3. make sure car information is displayed | User should be able to view more car details when a car is click from the list/table | Mouse Click SEARCH: BMW |  |  | pass
|  |  | CID02_T12_02 | 1. click a specific car 2. make sure car information is displayed and different to other cars | User should be able to view more car details when a car is click from the list/table | Mouse Click SEARCH: Toyota |  |  | pass
| T13 | Add counter to show total number of cars available | CID02_T13_01 | 1. Ensure counter is present - numbering the cars | User should be able to see counters on cars to see total number available/matching their search | Mouse Click |  |  | pass
| T14 | Verify story is complete | CID02_T14_01 | Ensure all task are complete for the story | Ensure all task are complete for the story | Mouse Click